Unforeseen Physical Conditions Notice (FIDIC 4.12 + 20.1)

[Date]

To: [Engineer's name and company]

Project: [Project name and contract reference]

Notice under Sub-Clause 4.12 and Notice of Claim under Sub-Clause 20.1

The Contractor gives notice under Sub-Clause 4.12 of the Conditions of Contract that physical conditions which the Contractor considers to have been Unforeseeable have been encountered on the Site.

The conditions were encountered on [date], at [location on the Site]. The conditions are as follows: [factual description — e.g., hard rock encountered at [depth] where the geotechnical information provided at tender indicated [what the tender information showed]]. The conditions are exposed for inspection and the Engineer is invited to examine them before they are covered.

These conditions are adversely affecting the progress of the Works: [affected activities and effect]. The Contractor also gives notice of claim under Sub-Clause 20.1 and claims an Extension of Time and Cost in accordance with Sub-Clause 4.12.

Detailed particulars will be submitted within [42] days in accordance with the Contract, or sooner if practicable. Contemporary records, including photographs and measurements of the conditions as encountered, are being maintained.

Yours faithfully,

[Name]

[Designation, for the Contractor]

Free template from chatnotice.app — AI-drafted FIDIC notices in minutes.